## Burndown Chart
How to use Burndown Chart
|  | Sprint Days | Ideal Line | Work Remaining
1 | Based on the Sprint duration days, populate Column "Sprint Days" | 0 | 300 | 300
2 | Based on your total team work (in hours) for the sprint, put the total number in E4 | 1 | 270 | 275
3 | Use the formula for E5 (and below) as shown below | 2 | 240 | 250
| `=Initial Work * (1 - (Day / Total Days)) | 3 | 210 | 240
| Initial work = E4 | 4 | 180 | 230
| Total Days as per 1 above | 5 | 150 | 220
4 | Populate the formula for all the days for E column | 6 | 120 | 180
5 | for the Work Remaining, start populating in column F based on the actual hours left | 7 | 90
6 | Once you start populating, the chart will automatically get updated. | 8 | 60
7 | Copy the sheet for each Sprint or for each Team | 9 | 30
|  | 10 | 0
Understanding the Data Structure
📌 Sprint Days (X-axis): Day 1 to Day 10 (Assuming a 2-week sprint)
📌 Ideal Line: A straight decline from start to finish
📌 Work Remaining (Y-axis): Hours remaining